## Team & Roles
Name | Student ID | Assigned Role | Main Responsibility
Cabir Eren Yıldırım | B2380.060093 | Project Manager | Project Planning, Time Tracking, Risk Management and Team Coordination.
Eyüp Tekne | B2280.060097 | Frontend Developer | User interface design, HTML/CSS coding.
Mert Hasan Yılmaz | B2280.060077 | Backend Developer | Database architecture, API development, and server-side coding.
Batuhan Yılmaz | B2280.060050 | Tester / QA & Backend Developer | Database architecture, API development, and server-side coding.& Error detection, writing test scenarios, and quality control.
Alperen Uslu | B2280.060065 | Frontend Developer & Documentation Specialist | User interface design, HTML/CSS coding.&Project reports, UML diagrams, and presentation preparation.

## Project Overview
Project Title | Campus Internship & Job Tracking System
Problem Statement: | Students wasting time searching for internship postings on different platforms and companies being unable to reach talent on campus directly and reliably.
Target Users: | Third- and fourth-year university students, company HR managers, school/career center managers.
Main Features: | 1- Student registration and CV upload module. 2- Companies' job posting and management module. 3- Job posting filtering/search system. 4- Admin (Teacher) job posting approval panel.

## Timeline
Week | Phase | Tasks
Week 1-2 | Initiation & Planning | Team setup, role assignment, Excel and Jira planning, Project Summary report.
Week 3-4 | Requirements & Design | Drawing UML Use Case diagrams, designing database tables, and creating user interface (UI) drafts.
Week 5-8 | Backend Development | Creating the database, writing the user login and ad posting APIs in Python.
Week 9-11 | Frontend Development | Coding web pages (HTML/Bootstrap) and connecting them to the backend.
Week 12-13 | Testing & QA | Testing the system with different roles (Student, Company), finding and fixing bugs.
Week 14 | Deployment & Closure | Completion of the project, preparation of the final report, and presentation to the instructor.

## Budget&Resources
Category: | Tool | Purpose
Project Management | Jira & Google Meet | Task Tracking and Communication
Design & Drafting | draw.io & MS Excel | UML diagrams and planning
Development (Code) | VS Code, Django & GitHub | Code writing and version control
Member | Role | Hours/Week
Eren Yıldırım | Project Manager &Backend Developer | 9 Hours
Eyüp Tekne | Frontend Developer | 7 Hours
Mert Hasan Yılmaz | Backend Developer | 7 Hours
Batuhan Yılmaz | Backend Developer & Tester /QA | 7 Hours
Alperen Uslu | Frontend Developer & Documentation | 7 Hours