## Team & Roles
Name | Student ID | Assigned Role | Main Responsibility
Cabir Eren Yıldırım | B2380.060093 | Project Manager | Project Planning, Time Tracking, Risk Management and Team Coordination.
Eyüp Tekne | B2280.060097 | Frontend Developer | User interface design, HTML/CSS coding.
Mert Hasan Yılmaz | B2280.060077 | Backend Developer | Database architecture, API development, and server-side coding.
Batuhan Yılmaz | B2280.060050 | Tester / QA & Backend Developer | Database architecture, API development, and server-side coding.& Error detection, writing test scenarios, and quality control.
Alperen Uslu | B2280.060065 | Frontend Developer & Documentation Specialist | User interface design, HTML/CSS coding.&Project reports, UML diagrams, and presentation preparation.

## Project Overview
Project Title | Campus Internship & Job Tracking System
Problem Statement: | Students wasting time searching for internship postings on different platforms and companies being unable to reach talent on campus directly and reliably.
Target Users: | Third- and fourth-year university students, company HR managers, school/career center managers.
Main Features: | 1- Student registration and CV upload module. 2- Companies' job posting and management module. 3- Job posting filtering/search system. 4- Admin (Teacher) job posting approval panel.
The Campus Internship & Job Tracking System is a centralized web-based platform designed to connect university students with companies offering internship and job opportunities. The system addresses the problem of students spending excessive time searching across multiple platforms while companies struggle to reach qualified campus talent directly. It serves senior university students, company HR representatives, and career center administrators. The platform enables students to create profiles and upload CVs, allows companies to post and manage job listings, provides search and filtering features for opportunities, and includes an administrative approval panel to ensure the reliability and safety of job postings.

## Timeline
Week | Phase | Tasks
Week 1-2 | Initiation & Planning | Team setup, role assignment, Excel and Jira planning, Project Summary report.
Week 3-4 | Requirements & Design | Drawing UML Use Case diagrams, designing database tables, and creating user interface (UI) drafts.
Week 5-8 | Backend Development | Creating the database, writing the user login and ad posting APIs in Python.
Week 9-11 | Frontend Development | Coding web pages (HTML/Bootstrap) and connecting them to the backend.
Week 12-13 | Testing & QA | Testing the system with different roles (Student, Company), finding and fixing bugs.
Week 14 | Deployment & Closure | Completion of the project, preparation of the final report, and presentation to the instructor.

## Budget&Resources
Category: | Tool | Purpose
Project Management | Jira & Google Meet | Task Tracking and Communication
Design & Drafting | draw.io & MS Excel | UML diagrams and planning
Development (Code) | VS Code, Django & GitHub | Code writing and version control
Member | Role | Hours/Week
Eren Yıldırım | Project Manager &Backend Developer | 9 Hours
Eyüp Tekne | Frontend Developer | 7 Hours
Mert Hasan Yılmaz | Backend Developer | 7 Hours
Batuhan Yılmaz | Backend Developer & Tester /QA | 7 Hours
Alperen Uslu | Frontend Developer & Documentation | 7 Hours